## Sheet 1
Table 1
Activity | Risk | Probability | Impact | Risk Score | Responsible
P1 - Define scope & objectives | Requirements are incomplete due to unclear legal rules | 2 | 8 | 16 | Project Manager
P1 - Define scope & objectives | Stakeholders disagree on compliance criteria | 3 | 7 | 21 | Project Manager
P2 - Map stakeholders | Key stakeholder available during analysis phase | 2 | 6 | 12 | Project Manager
P2 - Map stakeholders | Communication failures lead to wrong responsibility matrix | 3 | 5 | 15 | Project Manager
P5 - Governance approval | Delayed management sign-off | 3 | 8 | 24 | Project Manager
P5 - Governance approval | Budget re-estimation after approval | 2 | 7 | 14 | Project Manager
SA2 - Legal gap analysis | Misinterpretation of data-protection law requirements | 2 | 9 | 18 | System Analyst
SA2 - Legal gap analysis | External legal consultant not available in time | 1 | 6 | 6 | System Analyst
SA3 - Draft requirements | Poor documentation quality causes rework | 2 | 8 | 16 | System Analyst
SA3 - Draft requirements | Data security requirements omitted | 3 | 10 | 30 | System Analyst