## Sheet1
Agile Development Project (5 students: Owner, Master, 3x developers)
Owner/Customer | Scrum Master | Developers | What you need to do | To be Included in the report
Product vision |  |  | Discuss and develop a vision for the team's software product. Study vision statements of major companies Identify one competing product. | ✓
Proto-persona and scenario (one page) |  |  | Cretae a persona (generalize user), and identify a specific scenario for the development | ✓
User stories and epics |  |  | Implement a survey: Identify your target customer group, and collect user stories | ✓
Features |  |  | Breakdown the scenario to two or three self-containing product iterations (versions) Compare your feaures against the competing product | ✓
Product Backlog Items |  |  | Detail the iterations into implementable tasks according to priority | ✓
| SW architecture SW Design Test Driven design (TDD) |  | Identify SW architecture, SW Design, and hold a sprint planning meeting - selects highest priority items from the backlog Think how to test units and functions, before start coding | ✓
| Sprint_1 Backlog eg: core functions | PBI refinement ® Tasks and estimates | Sprint planning meeting - selects highest priority items from the backlog Avoid feature creep | List of PBIs for sprint 1
|  | scrum standup (15min) every other day | Report individually: what was done, what is being done, impediments Scrum master removes impediments | Scrum standup minutes
|  | Extreme programming Automated testing (optional) | Implement some XP practices (Incremental plannig, refactoring, Test-driven development ) | XP details
|  | DevOps (CICD) - GitHub | Development and Testing intertwined | CICD details
|  | Burndoown chart | Progress vs time remaining | ✓
|  | Customer feedback |  | ✓
| Sprint ends | check "decision of done" | Ready to release, Demonstration to the Owner/customer | none
| Sprint retrospective meeting |  | Is the What went well/wrong, what can be improved | meeting minutes
2-3 weeks
Backlog refinement
| Sprint_2 Backlog eg: user interface | PBI refinement ® Tasks and estimates | Sprint planning meeting - selects highest priority items from the backlog Avoid feature creep | List of PBIs for sprint 2
|  | scrum standup (15min) every other day | Report individually: what was done, what is being done, impediments Scrum master removes impediments | Scrum standup minutes
|  | Extreme programming Automated testing (optional) | Implement some XP practices (Incremental plannig, refactoring, Test-driven development ) | XP details
|  | DevOps (CICD) - GitHub | Development and Testing intertwined | CICD details
|  | Burndoown chart | Progress vs time remaining | ✓
|  | Customer feedback |  | ✓
| Sprint ends | check "decision of done" | Ready to release, Demonstration to the Owner/customer | none
| Sprint retrospective meeting |  | What went well/wrong, what can be improved | meeting minutes
check "decision of done"
2-3 weeks
Backlog refinement
| : | :
| : | :
2 months | End of Project |  | Submit a detailed repotr explaining items in the column E
Submit a 2minute product launch video of your product
Identify team members individual contribution to each task in the report
Poduct Owner | The customer
Idea of product evolution
Create, maintain, and prioratise the backlog
Scrum Master | Remove impediments
Bridge between owner and developers
Dev Team | Produce Iteration
No heirarchy
Equally responsible
Artifacts (documents) | Product backlog (user stories - expected features and functionality)
Sprint backlog
Product increment
Burndown chart